## 1. Product Overview
Field | Details
Product Name | AI Personal Finance Assistant
Product Vision / Purpose | To empower individuals to take control of their financial life by providing automated insights, smart budgeting
Business Goals / Key Success Factors | • Reduce user effort in tracking expenses through automation • Provide accurate, real-time financial analytics • Improve user savings behavior through personalized recommendations
Primary Stakeholders | frontend-saurya anand backened- Satyaprakash integeration and deploy-srinivas rc

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email and OTP so that I can access my account securely. | Registration screen details | Must Have | 8 | done | Backend Dev team | Verify registration with valid data | QA
|  |  |  | Pop-ups once registered |  |  |  |  | Check success pop-up
|  |  |  | Login screen |  |  |  |  | Validate login UI fields
Check OTP generated
OTP delivery success test
|  |  |  | Login Error Screen |  |  |  |  | Invalid OTP test
E1 | User Authentication | US2 | As a user, I want to log in using email so that I can securely access my account. | Login | Must Have | 5 | done | Backend Dev | Valid/Invalid login, OTP expiry | QA
E1 | User Authentication | US7 | As a user, I want my login session secured using JWT so that my data remains protected. | JWT tokens, Token expiry, Refresh token, Secure cookie storage | Must Have | 3 | done | Backend Dev | Token expiry test, Auth guard test | QA
E2 | Dashboard | US5 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. | Dashboard UI, Graphs, Analytics API | Should Have | 13 | done | Frontend Dev | Data loading test, Graph rendering | QA
E2 | Dashboard | US6 | As a user, I want my transactions to be categorized automatically so that I can understand my expenses. | Categorization logic, Category API, Manual edit option | Could Have | 8 | done | Backend Dev | Auto category accuracy, Manual update test | QA
E2 | Dashboard | US3 | As a user, I want to set budgets so that I can manage overspending. | Budget setup UI, Budget API, Alerts | Could Have | 5 | done | Frontend + Backend Dev | Budget trigger test, Alert visibility test | QA
E2 | Dashboard | US8 | As a user, I want to manually add a transaction so that I can record expenses or income not captured automatically. | Add Transaction UI (amount, date, category, notes), Save Transaction API, Input validation, Update analytics after addition | Should Have | 5 | done | Frontend + Backend Dev | Add valid transaction, required field test, analytics updated correctly | QA
E3 | dashboard | us9 | user get alert in dashboard | i | could have | 5 | to do | backend | send alert message to user
E4 | deployment,website protection |  | arject,vercel deployment |  | should have |  | to do | backened | to protect and publish the website
Notes: | MoSCoW | [9 empty] | ]\\
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features (List Epic Names) | Dependencies | Demo Status
v0.1 | 2025-11-15 | Authentication (E1), Dashboard MVP (E2) | None | completed
v0.3 | 2025-11-17 | Add Transaction (US8), Manual Category Edit, | Backend DB Setup | completed
v0.4 | 2025-11-26 | Budget Module (US3), Overspend Alerts, Dashboard Filters | Requires Notification System | completed
v0.5 | 2025-11-27 | Analytics Export (E2), Notification System | ai scanner | completed
v1.0 | 2025-11-30 | Full Dashboard v2, Monthly Reports, User Profile Settings | Stable APIs from all modules | completed
v1.1 | 2025-12-02 | Performance Optimization, UI Polishing, Minor Enhancements | QA Sign-off | completed
v1.1 | 2025-12-08 | deployment |  | completed
v0.2 | 2025-12-08 | Auto Transaction Categorization | Requires API Upgrade | completed

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items Next time what will you do differently
Team collaboration was great | Test coverage was low | Automate the test pipeline in the next sprint
Clear communication within the team | Requirements changed late in sprint | Improve requirement freeze and early validation
Good knowledge sharing | Lack of documentation clarity | Maintain structured API and feature documentation
Quick resolution of blockers | No dedicated time for code reviews | Allocate fixed code review slots daily
UI components were reusable and clean | Environment configuration issues | Standardize environment setup and maintain environment parity

## test result
Test Case ID | Scenario | Expected Result | Actual Result | Status
TC-001 | User logs in with valid credentials | Login successful, dashboard loads | As expected | PASS
TC-010 | Upload valid receipt image | Receipt stored, OCR triggered | As expected | PASS
TC-012 | Upload corrupted image | Error shown, no processing | Correct error shown | PASS
TC-020 | AI categorizes transaction | Category assigned | AI category mismatch for 2 items | FAIL
TC-035 | Create rule to categorize Amazon transactions | Matching transactions auto-tagged | Correct for 80% | FAIL
TC-055 | Dashboard loads monthly spending | Summary matches DB | As expected | PASS
test samples
Metric | Result
Total Test Cases | 120
Executed | 120
Passed | 108
Failed | 7
Blocked | 5
Pass Percentage | 90%